## Facility Name
Critical Facility Documents:
WR# Facility Name | [5 empty] | Critical Documents Review
Document Type |  | Document | Applicable to Site | Document Format | DFOM Notificaiton | Received | Document Date | Completed & Approved? | FCIS Notes | FCIS S Drive Location
Design Phase Documents | 1 | Basis Of Design (BOD), Approved for Construction | l | Electronic / Hardcopy | No
| 2 | Facility User Requirements Specification (URS) | l | Electronic Native / Hardcopy | Yes
| 3 | Design Drawings, Approved for Construction | l | Electronic Native / Hardcopy | Yes
| 4 | Specifications Manual, Approved for Construction | l | Electronic Native / Hardcopy | No
| 5 | Flow charts and Classification and Pressurization Diagram | l | Electronic Native / Hardcopy | Yes
| 6 | Risk Assessment (if applicable) | l | Electronic / Hardcopy | No
| 7 | cGMP Design Review Report (if applicable) | l | Electronic / Hardcopy | No
| 8 | System Level Impact Assessment (SLIA) | l | Electronic / Hardcopy | Yes
| 9 | Component Level Impact Assessment (CLIA) | l | Electronic / Hardcopy | Yes
| 10 | Type C Meeting Document (if applicable) | l | Electronic | No
Construction Phase Documents | 1 | Facility System/Equipment Factory Acceptance Test (FAT) - (if applicable) | l | Electronic / Hardcopy | No
| 2 | Facility System/Equipment Site Acceptance Test (SAT) - (If applicable) | l | Electronic / Hardcopy | No
| 3 | Shop Drawings/Submittals | l | Electronic | No
| 4 | Testing, Adjusting, and Balancing (TAB) Report | l | Electronic / Hardcopy | Yes
CQV Phase Documents | 1 | Commissioning Report | l | Electronic / Hardcopy | Yes
| 2 | Airflow Visualization Study (AVS) Video & Reports | l | Electronic / Hardcopy | No
| 3 | Calibration Records (Temp/Humidity and dP sensors) | l | Electronic | Yes
| 4 | HEPA Filter Certifications | l | Electronic | Yes
| 5 | Certification of PECs/BSC's | l | Electronic | No
| 6 | EMS Validation Documents | l | Electronic | No
| 7 | HVAC Qualification | l | Electronic / Hardcopy | No
| 8 | Validation Master Plan (VMP) - PVMP | l | Electronic | No
| 9 | Compressed Gas Qualification (CO2/CA/LN2) | l | Electronic | No
| 10 | Engineering Change Request Forms | l | Electronic | No
| 11 | Temperature/Humidity/dP/ACH - Set points and Alarms and Delays | l | Electronic / Hardcopy | Yes
| 12 | O&M Manuals | l | Electronic | Yes
| 13 | Record Drawings/As Builts | l | Electronic Native / Hardcopy | Yes
| 14 | Record Specifications Manual | l | Electronic Native / Hardcopy | No
| 15 | Training Documents & Videos | l | Electronic / Hardcopy | Yes
| 16 | Control Documentation (P&IDS’s, Sequence of Operation, Logic Diagram) | l | Electronic Native / Hardcopy | Yes
| 17 | Backup Software Programs for applicable control systems | l | Electronic Native | Yes
| 18 | Spare Parts List | l | Electronic | Yes
|  | Official Turnover date from Construction (DDCM) to DFOM | l | Email / Electronic | Yes
|  |  | l | Document applies to this APF
|  |  | l | Document does NOT apply to this APF